## Sprint 1
Functional Testing Case Study
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report http://demowebshop.tricentis.com/ Module: REGISTRATION, LOGIN & BUY ITEMS
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Depndacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Demo web shop is the sample online application for buying items It supports various functionalities such as user registration, login, searching for a product, add items to cart and payments. It is developed by Tricentis. It supports multiple browsers such as IE, Firefox, Chrome. In scope Functionality: Demo webshop provides following functionalities to the end user : 1. Registration Page : Validate the Firstname, Lastname, Email, Password, Retype password on the page. 2. Login a. Email : validate all fieldsa with valid and invlaid data. b. Password : validate with all options - valid and invlaid; the forgot password link, Sign-up link 3. Search an item a. Search Product on various categories - Books, Electronics items, Apparels and shoes, Digital downloads, and Jewellary b. View the products availability c. Add to cart 4. Buy items a. Enter shipping address b. Enter billing address c. Enter the payment details d. Enter the mode of delivery e. Discount coupons 5. Confirm Booking a. Download and acknowledge the receipt Out of Scope Functionality: 1. Cancel the order 2. Any other functionalities Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## user stories
Issue Type | Summary | Priority | Story Assignee
Epic 1 verify registration functionality | As a user, I should be able to register the website so that user can login on url | Critical | Lakshmi durga bhavani
story1 verify wheather user can register | As a new user,I should be able to sign up so that I can access the portal easily | High
Story 2 Verify whethe user can signup on all version | As a user, I want to access webshop on version like firefox,chrome | High
Story 3 Verify whether user can acess application on all devices | As a user, I want to access DemoWebshop on versions like Firefox, Google Chrome and so on from windows so that I can access the portal with all credentials | High
Story 4 Verify whethather user is able to gender | As,a user ,I want to select the gender | High
story 5 Verify whethather user is able to selec gender with buttons | As,a user ,I want to select the gender | high
Story 6 Verify whethather user is able to add Firstname | As a new user, I should be able to enter Firstname | High
Story 7 Verify whetheruser is able to add Lastname | As a new user,I should be able to Lastname | High
story 8 verify use enter email adress | As a user ,I should able to enter email adress | High
Story 9 verify wheather user is able to enter password | As a user,I should be able to confirm password | High
Story 10 verify the confirm password | As a user,I should be able to enter to loginpage | High
St
Epic 2 Verify login functionality | As a user,user should be able to login through the website http://demowebshop.tricentis.com/login | Critical | Rakkesh R
Story 1 Verify whether user is able to login to the application with valid credentials | As a user, I should be able to login to the application using valid email and and password | High
Story 2 Verify whether user will not be able to login with invalid credentials | As a user, I should receive an error message whenever I enter invalid email and password | High
Story 3 Verify whether user can login on all versions | As a user, I want to access DemoWebshop on versions like Firefox, Google Chrome and so on from windows so that I can access the portal with all credentials | High
Story 4 Verify whether user can access application on all devices | As a user, I want to login on DemoWebshop so that I can access all the devices on the application | High
Story 5 Verify when user forgot password | As a user, If I forget my password, I should be able to reset password by clicking on forgot your password link and it should redirect me to forgot password page. Then I should be able to reset my password by providing my email id and I should receive password reset link in email. Then, by accessing the password link, I should be able to reset my password. Lastly I have to get an error message when I select a new password without a special character. | High
Story 6 Verify when user press recover without entering email in forgot password get error message | As a user, I should get error message when I click on recovery with out entering the email in password recovery | High
story 7 verify whether the user is able to select remember me checkbox | As a user ,I am able to select remember me check box | High
story 8 verify that the logout link is redirected to login/homepage | As a user ,I am able to click logout link which will be redirected to login/home page | High
story 9 verify that the user is redirected to appropriate page after successful login | As a user i am able to redirected to appropriate page after successful login | High
Story 10 verify that the spaces should not be allowed while setting password | As a user , spaces should not be allowed while setting password | High
Story 11 Verify that the user is not able to login with blank email and password | As a user, I am not able to login with blank email id and password | High
Story 12 Verify that the user is not able to login with valid email id and invalid password | As a user , I am not able to login with valid e mail id and invalid password | High
Story 13 Verify that the user is not able to login with valid password and invalid email id | As a user , I am not able to login with valid password and invalid email id | High
Epic 3 Verify Search functionality | As a user, I should be able to access search bar to search on the website | Critical | Ramya Barathi
Story 1 Verify Whether search bar is available or not | As a user, I should be able to access search bar to search any product from the website | High
Story 2 Verify Whether search functionality is working or not for any product | As a user, I should be able to search any product through search bar | High
Story 3 Verify wheter it is auto suggesting the words while typing in search field | As a user, I should be able to search any product through search bar with Suggestion | High
Stoty 4 Verify whether it is able to accept Capital and Small letter for search | As a user, I should be able to search with Capital and Small letter for product | High
Story 5 Verify whether it is having "Search store" as default keyword at search box | As a user, I should be able to see "Search store" as default keyword at search box | High
Story 6 Verify whether Searched product is displaying appropriate result or not | As a user, I should be able to see Searched product is displaying appropriate result or not | High
Story 7 Verify whether when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | As a user, I should be able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | High
Stotry 8 Verify whether when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | As a user, I should be able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | High
Story 9 Verify whether we click on Search bar with out any key word it is showing error message as "Please enter some search keyword". | As a user, I should be able to get error message as Please enter some search keyword when click on Search bar with out any key word | High
Story 10 Verify whether Search is showing error message when the user searching for unrelated data. | As a user, I should receive a error message "No records matched your search criteria" when the user searching for unrelated data | High
Product Module
Epic 6 Verify user is able to place the order | As a user, I should be able to place the order. | Critical | Ramya G
Story 1 Verify whether user is able place the order. | As a user, I should be able to place the order. | High
Epic 7 Verify Shipping Details | As a user, I should be able to add shipping details. | Critical | Ramya G
Story 1 Verify whether user is able to add Firstname | As a user, I should be able to add Firstname to the shipping details page. | High
Story 2 Verify whether user can add last name | As a user, I should be able to add Last name to the shipping details page. | High
Story 3 Verify whether user is able to add valid Mobile number | As a user, I should be able to add Mobile number to the shipping details page. | High
Story 4 Verify whether user adds invalid Mobile number | As a user, I should receive an error message if invalid mobile number is entered. | High
Story 5 Verify whether user is able to add shipping address | As a user, I should be able to add shipping address to the shipping details page. | High
Story 6 Verify whether user is able to submit shipping details. | As a user, I should be able to submit the shipping details. | High
Epic 8 Verify payment functionality | As a user, I should be able to place a order throuhg payment | Critical | Ramya G
Story 1 Verify whether the payment is successful | As a user,I should be able to do payment successfully. | High
Story 2 Verify whether the user is cannot proceed to payment | As a user,I should receive a message like cannot proceed to payment | High
Story 3 Verify whether the payment is successful on cod | As a user,I should be able to do payment is successful on cod | High
Epic 9 Verify cancel the order | As a user, I should be able to cancel order | High | Ramya G
Story Verify whether user is able to cancel the order | As a user,I should be able to cancel/remove order | High
Receipt Module
Story 1 | As a user I want to download the receipt | High | Raghav Khanna
Story 2 | As a user I want to print the receipt | High
Story 3 | As a user, I want to acknowlege the purchase | High
Story 4 | As a user, I want to verify that can we download receipt before payment | High
Story 5 | As a user, I want to verify that user is able to download the receipt before payment | High
Story 6 | As a user, I want to verify that download button is functioning or not | High
Story 7 | As a user, I want to verify that print button is functioning or not | High
Registration Module
Login Module
Search Module

## Requirements
Requirement ID | Requirement Description
DW_1 | User should be able to Sign Up. for sign up user needs gender,Firstname ,lastname emailadrees
DW_2 | User should be able to Login. for logIn user needs Username Password
DW_3 | User should be able to Search product.
DW_4 | User should be able to view product as well the product description.
DW_5 | User should be able to add/remove product from cart.
DW_6 | User should be able to place the order.
DW_7 | User should be able to add shipping details. for shipping user needs to update FirstName LastName MobileNo Address
DW_8 | User should be able to choose payment option. COD CardPayment
DW_9 | User should be able to cancel the order.
DW_10 | User should be able to access contact section. For contact user needs to fill query details Full Name MobileNo Email
DW_11 | User should be able to give a review to a particular product.
DW_12 | User is able to download the receipt after placing the order
DW_13 | User can acknowleged about the purchase

## Test_Scenario
Epic Name | Story Name | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
Epic 1 verify registration functionality | story1 Verify Wheather user can able to login | TS_DEMO_1 | REQ_DW_01 | To Verify Wheather url of website to its redirecting to landing page or not | FUNCTIONAL TESTING | 1 | validate that user can login to the page is available or not
| story2 Verify Wheather user can able to register | TS-DEMO-2 |  | To verify Wheather url of website to its redirecting to landing page or not | FUNCTIONAL TESTING | 1 | validate that user can register to the page is available or not
| story3 verify that user able to sign up so that we can acess the portal easily | TS-DEMO-3 |  | To verify that user able to sign up so that we can acess the portal easily | FUNCTIONAL TESTING | 1 | validate that user able to sign up so that we can acess the portal easily or not
| story 4 validate user can acess on all veersion like firefox,chrome | TS-DEMO-4 |  | to verify user can acess on all version like firefox,chrome.. | FUNCTIONAL TESTING | 1 | validate user can acess on all veersion like firefox,chrome or not
| story 5 validate that user can select gender | TS_DEMO_5 |  | to verify that user can select gender | FUNCTIONAL TESTING | 1 | validate that user can select gender or not
| story 6 validate that user can select gender with radio | TS-DEMO-6 |  | to verify that user can select gender with radio buttons | FUNCTIONAL TESTING | 1 | validate that user can select gender or not
| story 6validate that user can enter firstname | TS-DEMO-7 |  | to verify that user can enter firstname | FUNCTIONAL TESTING | 1 | validate that user can enter firstname or not
| story 7 validate that user can enter lastname | TS-DEMO-8 |  | to verify that user can enter lastname | FUNCTIONAL TESTING | 1 | validate that user can enter firstname or not
| story 8 validate that user add user email adress | TS-DEMO-9 |  | to verify that user can enter email address | FUNCTIONAL TESTING | 1 | validate that user can enter email or not
| story 9validate that user to enter password | TS_DEMO_10 |  | to verify that user add password | FUNCTIONAL TESTING | 1 | validate that user add password or not
| story 10 validate that user can confirm password | TS-DEMO-11 |  | to verify that user can enter loginpage | FUNCTIONAL TESTING | 1 | validate that user can enter loginpage or not
Epic 2 Verify login functionality | Story 1 Verify whether user is able to login to the application with valid credentials | TS_DEMO_12 | REQ_DW_02 | To Verify users can login by entering valid credentials | FUNCTIONAL TESTING | 1 | Validate users can login by entering valid credentials
| Story 2 Verify whether user is not able to login to the application with valid credentials | TS_DEMO_13 |  | To Verify user cannot login by entering invalid credentials | FUNCTIONAL TESTING | 2 | Validate user cannot login by entering invalid credentials
| Story 3 Verify user can reset password by using forgot password | TS_DEMO_14 |  | To Verify user can reset by using the forgotten password link | FUNCTIONAL TESTING | 1 | Validate user can reset by using the forgotten password link
| Story 4 Verify user can get password reset link to his/her mail address | TS_DEMO_15 |  | To Verify user can get the reset password link on the registered email ID. | FUNCTIONAL TESTING | 1 | Validate user can get the reset password link on the registered email ID.
| Story 5 Verify user's password reset link has access to reset the password | TS_DEMO_16 |  | To Verify user's password reset link has access to reseting the password | FUNCTIONAL TESTING | 1 | Validate user's password reset link has access to reseting the password
| Story 6 Verify user get an error message when selecting new password without special characters | TS_DEMO_17 |  | To Verify user gets an error message when they make the new password without special characters | fUNCTIONAL TESTING | 1 | Validate user gets an error message when they make the new password without special characters
| story 7 verify whether the user is able to select remember me checkbox | TS-DEMO-18 |  | To verify wheather the user is able to select remember me checkbox | FUNCTIONAL TESTING | 1 | validate that whether the user is able to select remember me checkbox
| story 8 verify that the logout link is redirected to login/home page | TS-DEMO-19 |  | To verify that the logout link is redirected to login/homrpage | FUNCTIONAL TESTING | 1 | validate that the logout link is redirected to login/home page
| story 9 verify that the user is redirected to appropriate page after successful login | TS-DEMO-20 |  | To verify that the user is redirected to appropriate page after successful login | FUNCTIONAL TESTING | 1 | validate that the user is redirected to appropriate page after successful login
| Story 10 verify that the spaces should not be allowed while setting password | TS-DEMO-21 |  | To verify that the spaces should not be allowed while setting password | FUNCTIONAL TESTING | 1 | validate that the spaces should not be allowed while setting password
| Story 11 Verify whether the user is not able to login with blank email id and password | TS-DEMO-22 |  | Verify whether the user is not able to login with blank email id and password | FUNCTIONAL TESTING | 1 | Validate whether the user is not able to login with blank email id and password
| Story 12 Verify whether the user is not able to login with valid email id and invalid password | TS-DEMO-23 |  | Verify whether the user is not able to login with valid email id and invalid password | FUNCTIONAL TESTING | 1 | Validate whether the user is not able to login with valid email id and invalid password
| Story 13 Verify whether the user is not able to login with invalid email id and valid password | TS-DEMO-24 |  | Verify whether the user is not able to login with invalid email id and valid password | FUNCTIONAL TESTING | 1 | Validate whether the user is not able to login with invalid email id and valid password
Epic 3 Verify Search functionality | Story 1 Verify Whether search bar is available or not | TS_DEMO_25 | REQ_DW_03 | To verify the Search bar is available or not | Functional Testing | 1 | Validate the Search bar is available or not
| Story 2 Verify Whether search functionality is working or not for any product | TS_DEMO_26 |  | To Verify Whether search functionality is working or not for any product | Functional Testing | 1 | Validate the Searched product is available or not
| Story 3 Verify wheter it is auto suggesting the words while typing in search field | TS_DEMO_27 |  | To Verify wheter it is auto suggesting the words while typing in search field | Functional Testing | 1 | Validate wheter it is auto suggesting the words while typing in search field
| Stoty 4 Verify wheter it is able to accept Capital and Small letter for search | TS_DEMO_28 |  | To Verify wheter it is able to search with Capital and Small letter for product | Functional Testing | 1 | Validate wheter it is able to search with Capital and Small letter for product
| Story 5 Verify wheter it is having "Search store" as default keyword at search box | TS_DEMO_29 |  | To Verify wheter it is to see "Search store" as default keyword at search box | Functional Testing | 1 | Validate wheter it is to see "Search store" as default keyword at search box
| Story 6 Verify whether Searched product is displaying appropriate result or not | TS_DEMO_30 |  | To Verify wheter it is able to see Searched product is displaying appropriate result or not | Functional Testing | 2 | Validate wheter it is able to see Searched product is displaying appropriate result or not
| Story 7 Verify whether when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | TS_DEMO_31 |  | To Verify wheter it is able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | Functional Testing | 1 | Validate wheter it is able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page
| Stotry 8 Verify whether when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | TS_DEMO_32 |  | To Verify wheter it is able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | Functional Testing | 1 | Validate wheter it is able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product
| Story 9 Verify whether we click on Search bar with out any key word it is showing error message as Please enter some search keyword. | TS_DEMO_33 |  | To Verify wheter it is able to get error message as Please enter some search keyword when click on Search bar with out any key word | Functional Testing | 1 | Validate wheter it is able to get error message as Please enter some search keyword when click on Search bar with out any key word
| Story 10 Verify whether Search is showing error message when the user searching for unrelated data. | TS_DEMO_34 |  | To Verify whether Search is showing error message when the user searching for unrelated data. | Functional Testing | 1 | Validate whether Search is showing error message when the user searching for unrelated data.
Epic 4 Verify view functionality | As a user, I should be able to view complete description of any product | TS_DEMO_35 | REQ_DW_04 | To verify user is able to view the product. | Functional Testing | 1 | Validate the products are visible to user.
Epic 5 Verify User is able to add/remove product from cart. | As a user, I should be able to add product to the cart. | TS_DEMO_36 | REQ_DW_05 | To verify user is able to add the product to cart or not. | Functional Testing | 2 | Validate the product gets added to cart.
| As a user, I should be able to remove product from cart. | TS_DEMO_37 |  | To verify user is able to remove the product from cart or not. | Functional Testing | 2 | Validate the product gets removed from cart.
Epic 6 Verify user is able to place the order | As a user, I should be able to place the order. | TS_DEMO_38 | REQ_DW_06 | To verify the order is placed or not. | Functional Testing | 2 | Validate order got placed or not.
Epic 7 Verify Shipping Details | As a user, I should be able to add Firstname to the shipping details page. | TS_DEMO_39 | REQ_DW_07 | To verify the user enters the first name. | Functional Testing | 2 | Validate the user has enter the first name.
| As a user, I should be able to add Last name to the shipping details page. | TS_DEMO_40 |  | To verify the user enters the last name. | Functional Testing | 2 | Validate the user has enter the last name.
| As a user, I should be able to add Mobile number to the shipping details page. | TS_DEMO_41 |  | To verify the user enters the valid mobile number or not. | Functional Testing | 3 | Validate the user enters the mobile number properly.
| As a user, I should receive an error message if invalid mobile number is entered. | TS_DEMO_42 |  | To verify the user enters all the required address fields. |  | 4 | Validate the user enters the mobile number properly.
| As a user, I should be able to add shipping address to the shipping details page. | TS_DEMO_43 |  | To verify the user enters all the shipping details or not. | Functional Testing | 9 | Validate the user enters the shipping details.
Epic 8 Verify payment functionality | As a user,I should be able to do payment successfully. | TS_DEMO_44 | REQ_DW_08 | To verify user is able to select CardPayment | Functional Testing | 4 | Validate the user is able to select payment option between CardPayment.
| As a user,I should receive a message like cannot proceed to payment | TS_DEMO_45 |  | To verify user is able to select COD | Functional Testing | 1 | Validate user is able to select COD payment option.
Epic 9 Verify cancel the order | As a user,I should be able to cancel/remove order | TS_DEMO_46 | REQ_DW_09 | To verify user is able to cancel the order or not. | Functional Testing | 1 | Validate user is able to cancel order.
Epic 5 Download the receipt | story1 As a user I want to download the receipt | TS_DEMO_47 | REQ_SU_10 | To verify that the user is able to download the receipt after the payment | Functional Testing | 1 | Validate regarding the receipt download
| Story 2 As a user I want to print the receipt | TS_DEMO_48 |  | To verify that the user is able to print the receipt from the website itself | Functional Testing | 1 | Validate regarding the printing the receipt
| Story 3 As a user I want to acknowledge the purchase | TS_DEMO_49 |  | To verify that the user is able to crosscheck the purchase | Functional Testing | 1 | Validate regarding the crosschecking of purchase
| Story 4 As ,a user that the user is not able to download the receipt before payment | TS_DEMO_50 |  | To verify that the user is not able to download the receipt before payment | Functional testing | 1 | validate that the user is not able to download the receipt before payment
| Story 5 As user is able to download the receipt before payment | TS_DEMO_51 |  | To verify that user is able to download the receipt before payment | functional testing | 1 | validate that user is able to download the receipt before payment
| story 6 As a user, I want to verify that download button is functioning or not | TS_DEMO_52 |  | to verify that download button is functioning or not | functional testing | 1 | validate that download button is functioning or not
| Story 7 As verify that print button is functioning or not | TS_DEMO_53 |  | To verify that print button is functioning or not | functional testing | 1 | validate that print button is functioning or not
RegistrationModule
Login Module
Login Module
Search Module
Product Module
Receipt Module

## Test Case Template
Testcase id | Requirment id | Test scenario | Pre Condition | Test Condition | Test Cases Steps | Test Data | Expected Results | Actual Result Iteration 1 | Status Iteration 1
TS_DEMO_1 | REQ_DW_01 | To verify wheather user can able to login and register using url | user should be in the website page | to validate if the url redirects to the correct page | select the url and site got displayed page login on url | URL | The url got selected and site got displyed | User is able to login and register | pass
TS_DEMO_2 |  | To verify wheather user can able to login and register using url | user should be in the website page | to validate if the url redirects to the correct page | select the url and site got displayed page register | URL | The url got selected and site got displyed | User is able to login and register | pass
TS_DEMO_3 |  | To verify wheather user can able to login and register using url | user should be in the website page | to validate if the url redirects to the correct page | select the url and site got displayed page acess on all devices | URL | The url got selected and site got displyed | User is able to login and register | pass
TS_DEMO-4 |  | To verify wheather user can able to login and register using url | user should be in the website page | to validate if the url redirects to the correct page | select the url and site got displayed page versions | URL | The url got selected and site got displyed | User is able to login and register | pass
TS-DEMO-5 |  | To verify wheather user can able to fill details or not | user should able to fill the details | to validate that user can enter details | select the gender | emailid:abc@gmail.com | gender is got selected and validated | user is able to select details | pass
TS-DEMO-6 |  | To verify wheather user can able to fill details or not | user should able to fill the details | to validate that user can enter details | when selecting the gender the radio button should able to select only one value | emailid:abc@gmail.com | gender is got selected and validated | user is able to select gender | pass
TS-DEMO-7 |  | To verify wheather user can able to fill details or not | user should able to fill the details | to validate that user can enter details | select the firstname | emailid:abc@gmail.com | the firstname got selected and validated | user is able to enter details | pass
TS-DEMO-8 |  | To verify wheather user can able to fill details or not | user should able to fill the details | to validate that user can enter details | select the lastname | emailid:abc@gmail.com | the lastname got selected and validatred | user is able to enter details | pass
TS-DEMO-9 |  | To verify wheather user can able to fill details or not | user should able to fill the details | to validate that user can enter details | select the email adsrees | emailid:abc@gmail.com | email adress got selected and validated | User is able to enter details | pass
TS-DEMO-10 |  | To verify that user can able to add password | user should able to enter email adrees | to validate that user can add password details | enter password details enter password | password:*** | password entered | user is able to enter password details | pass
TS-DEMO-11 |  | To verify that user can able to add password | user is able to enter confirm password | to validate that user can enter password details | enter password details confirm password | password:xxx | confirmation of password | User is able to enter confrim password details | pass
TC_DEMO_12 | REQ_DW_02 | To verify whether url of the website is redirected to landing page or not | User should be in the Website page | To validate if the url redirects to the correct page | Select the url and site got displayed | Url | The url got selected and site got displayed | The Url and site got displayed | pass
TC_DEMO_13 |  | To verify if user is able to login with valid credentials | User must be in the Login Page | To validate if user is able to login with valid credentials | 1.Enter the Email ID 2.Enter the Password | 1.Email id: rakkesh@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated | User is able to Login Successfully | pass
TC_DEMO_14 |  | To verify that user is not able to login with Invalid credentials | User must be in the Login Page | To Validate if user is not able to login with invalid credentials | 1.Enter the Email ID 2.Enter the Password | 1.Email id: rock@gmail.com 2.Password:***** | 1.The Email is validated 2.The password is validated | User is not able to login and displays error message | pass
TC_DEMO_15 |  | To verify that user is not able to login with blank email id and password | User must be in the login page | To validate that user is not able to login with blank email id and password | 1.Enter the Email ID 2.Enter the Password | 1.Email id: 2.Password: | 1.The Email is validated 2.The password is validated | User is not able to login and displays error message | pass
TC_DEMO_16 |  | To verify that user is not able to login with valid email id and invalid password | User must be in the login page | To validate that user is not able to login with valid email id and invalid password | 1.Enter the Email ID 2.Enter the Password | 1.Email id: rakkesh@gmail.com 2.Password:**** | 1.The Email is validated 2.The password is validated | User is not able to login and displays error message | pass
TC_DEMO_17 |  | To verify that user is not able to login with Invalid email id and valid password | User must be in the login page | To validate that user is not able to login with Invalid email id and valid password | 1.Enter the Email ID 2.Enter the Password | 1.Email id: rock@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated | User is not able to login and displays error message | pass
TC_DEMO_18 |  | To verify if user is able to reset password | User must be in the Password recovery Page | To validate if the user is able to reset his password or not | 1.Click Forget password Link 2.Enter the Email ID 3.Get the reset link to mail and access link 4.Enter New Password | 1.Email id: rakkesh@gmail.com 2.Resetlink: 3.New Password:**** | 1. The Email ID got entered 2.The Reset Link is sent to email 3.New Password is set | User is able to reset password successfully | pass
TC_DEMO_19 |  | To verify whether the user is able to select Remember me Check box | User must be in the Login Page | To validate whether the user is able to select Remember me Check box | 1.Enter the Email ID 2.Enter the Password 3.Click Remember me Check box | 1.Email id: rakkesh@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated 3.Remember me check box is validated | User is able to Login | pass
TC_DEMO_20 |  | To verify that the logout link is redirected to login/home page | User must be in the profile Page | To validate that the logout link is redirected to login/home page | 1.Click On Logout link | N/A | The user can able to logout when clicking logout link | User is able to logout successfully | pass
TC_DEMO_21 |  | To verify that User is redirected to appropriate page after successful login | User must be in the profile Page | To validate that User is redirected to appropriate page after successful login | 1.Enter the Email ID 2.Enter the Password 3.Click Login | 1.Email id: rakkesh@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated | User is successfully redirected to profile page | pass
TC_DEMO_22 |  | To verify that the User should be able to login with the new password after changing the password | User must be in the Login Page | To validate that the User should be able to login with the new password after changing the password | 1.Enter the Email ID 2.Enter the Password 3.Click Login | 1.Email id: rock@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated | User is successfully able to login with new password | pass
TC_DEMO_23 |  | To verify that the user should not be able to login with the old password after changing the password | User must be in the Login Page | To validate that the user should not be able to login with the old password after changing the password | 1.Enter the Email ID 2.Enter the Password 3.Click Login | 1.Email id: rock@gmail.com 2.Password:***** | 1.The Email is validated 2.The password is validated | User is not able to login with old password after changing the password | pass
TC_DEMO_24 |  | To verify that spaces should not be allowed while setting password | User must be in the Login Page | To validate that spaces should not be allowed while setting password | 1.Enter the Email ID 2.Enter the Password 3.Click Login | 1.Email id: rakkesh@gmail.com 2.Password:*** | 1.The Email is validated 2.The password is validated | User is not allowed to set password with spaces | pass
TS_DEMO_25 | REQ_DW_03 | To verify the Search bar is available or not | User should be logged into the site | To Validate the Search bar is available or not | 1.Should be on home page of web shop site 2.Click on Search bar option | N/A | User is able to search the product using search bar | User is able to search the product using search bar | Pass
TS_DEMO_26 |  | To Verify Whether search functionality is working or not for any product | User should be access the search bar | To Validate the Searched product is available or not | 1.Click on Search bar option 2.Search for the product | Product Name:Smartphone | User can see whether the product searched using search bar is available | User can see whether the product searched using search bar is available | Pass
TS_DEMO_27 |  | To Verify wheter it is auto suggesting the words while typing in search field | User should be access the search bar | To Validate wheter it is auto suggesting the words while typing in search field | 1.Click on Search bar option 2.Search for the product | Product Name:Smar | User can see whether the product searched using search bar is auto suggesting a product or not | User can see whether the product searched using search bar is auto suggesting a product or not | Pass
TS_DEMO_28 |  | To Verify wheter it is able to search with Capital and Small letter for product | User should be access the search bar | To Validate wheter it is able to search with Capital and Small letter for product | 1.Click on Search bar option 2.Search for the product | Product Name:SMART PHONE Product Name:Smartphone | User can see whether the product searched using search bar is available | User can see the product searched using search bar is available | Pass
TS_DEMO_29 |  | To Verify wheter it is able to see "Search store" as default keyword at search box | User should be access the search bar | To Validate wheter it is able to see "Search store" as default keyword at search box | 1.Be in Home page Demowebshop | N/A | User can see whether the search bar box containing default value "Search store" | User can see the search bar box containing default value "Search store" | Pass
TS_DEMO_30 |  | To Verify wheter it is able to see Searched product is displaying appropriate result or not | User should be access the search bar | To Validate wheter it is able to see Searched product is displaying appropriate result or not | 1.Click on Search bar option 2.Search for the product | Product Name:Cell phone | User can able to see Searched product is displaying appropriate result | User cannot able to see appropriate result | Fail
TS_DEMO_31 |  | To Verify wheter it is able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | User should be access the search bar | To Validate wheter it is able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | 1.Click on Search bar option 2.Search for the product | Product Name:Smartphone | User can able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | User can able to see when we enter the key word and click on Search bar it will show search field with the features as Advanced Search in display page | Pass
TS_DEMO_32 |  | To Verify wheter it is able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | User should be access the search bar and Advanced Search in display page | To Validate wheter it is able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | 1.Click on Search bar option 2.Search for the product 3.Click on Advanced Search in display page | Product Name:Smartphone | User can able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | User can able to see when we click on Advanced Search in display page it is showing the Manufacturer and price range for the product | Pass
TS_DEMO_33 |  | To Verify wheter it is able to get error message as "Please enter some search keyword "when click on Search bar with out any key word | User should be access the search bar | To Validate wheter it is able to get error message as Please enter some search keyword when click on Search bar with out any key word | 1.Click on Search button | N/A | User can able to get error message as Please enter some search keyword when click on Search bar with out any key word | User can able to get error message as Please enter some search keyword when click on Search bar with out any key word | Pass
TS_DEMO_34 |  | To Verify whether Search is showing error message when the user searching for unrelated data. | User should be access the search bar | To Validate whether Search is showing error message when the user searching for unrelated data. | 1.Click on Search bar option 2.Search for the product | Product Name:Wire | User can see when the product searched using search bar is not available and getting error message or not | User can see when the product searched using search bar is not available and getting error message or not | Pass
TC_DEMO_35 | REQ_DW_04 | To verify user is able to add the product to cart or not. | To validate user able to add the product to cart. | To validate user able to add the product to cart. | 1. Click on the product name. 2. Click on "Add to Cart" option. | Product Name: Samsung Galaxy S6 | The product gets added to the cart. | Product is getting added to cart | Pass
TC_DEMO_36 | REQ_DW_05 | To verify user is able to remove the product from cart or not. | To validate user able to remove the product from cart. | To validate user able to remove the product from cart. | 1. User should be on the home page of Demoblaze. 2. Click on "Cart" option. 3. Click on the "Delete" option of which product wants to be removed. | Product Name: Samsung Galaxy S6 | The product gets removed from the cart. | User is not able to remove the product from cart. | Fail
TC_DEMO_37 | REQ_DW_06 | To verify the order is placed or not. | To validate the order have been placed or not | To validate the order have been placed or not | Click on "Place order" button to place order | N/A | Once pressed "Place order" button, user should be redirected to shipping details page | Order is getting placed | Pass
TC_DEMO_38 | REQ_DW_07 | To verify the user enters the first name, last name and mobile number. | To validate the first name, last name and mobile number is entered or not. | To validate the first name, last name and mobile number is entered or not. | 1. Click on the "Place order" button from cart. 2. Enter the following details required. First name Last name Mobile number | First name: User1 Last name: xyz Mobile number: 9876543210 | The entered details will be displayed. | User gets directed to enter the address details. | Pass
TC_DEMO_39 | REQ_DW_07 | To verify the user enters all the required address fields. | To validate the adress is properly entered or not. | To validate the adress is properly entered or not. | 1. Enter Street name 2. Enter City 3. Enter State 4. Enter Pin Code | 1. Street name: 970 Stuart Street 2. City: ZAVALLA 3. State: Texas 4. Pincode: 75980 | The entered details will be displayed. | Address added succesfully | Pass
TC_DEMO_40 | REQ_DW_07 | To verify the user enters all the shipping details or not. | To validate the details entered by the user are correct | To validate the details entered by the user are correct | Click on "Save" button after confirming all the details are correct or not. | N/A | The entered details will be saved for further delivery. | Details entered are saved succesfully | Pass
TC_DEMO_41 | REQ_DW_08 | To verify user is able to select CardPayment | To validate the card payment for the order | To validate the card payment for the order | 1. Enter Name on Card 2. Enter Card Number 3. Enter expiry date 4. Enter CVV | 1. Name on Card: ABC DEF 2. Card Number: 1234 1234 1234 1234 3. Expiry date: 11/22 4. CVV: 123 | The entered details are used to make payment and order has been placed and system shows payment reciept. | User is able to make payment inspite of invalid card number | Fail
TC_DEMO_42 | REQ_DW_08 | To verify user is able to select COD | To validate whether COD is applicable or not | To validate whether COD is applicable or not | Select COD in payment method | N/A | Display entered payment method is COD and order has been placed and system shows payment reciept. | User is able to place order after selecting COD | Pass
TC_DEMO_43 | REQ_DW_09 | To verify user is able to cancel the order or not. | To validate user is able to cancel the order or not | To validate user is able to cancel the order or not | Click on "Cancel order" button from Review | N/A | Order is Cancelled. | User is not able to cancel the product. | Fail
TC_DEMO_44 | REQ_DW_10 | To verify how will the user can download the receipt after the purchase | User should be at the checkout page | To validate that user is able to download the receipt | Download the receipt | Receipt will be downloaded | The order receipt will be downloaded | Receipt download | Pass
TC_DEMO_45 | REQ_DW_11 | Print the purchase receipt | User had must a valid purchase id | User will be able to print the purchase receipt from the checkout page | User will able to print the receipt from the printer button | Printing of receipt | Purchase receipt will be printed | Able to print | Pass
TC_DEMO_46 |  | Verify the acknowledge of the purchase | User must have the valid order id | User must have the valid order id where they can verify the purchase | User should acknowledge that purchase by order id | Valid order id | Acknowledment message appers | Purchase acknowleded | Pass
TC_DEMO_47 |  | To verify that the user is not able to download the receipt before payment | User must had to make the payment first | User must have a valid payment id to verify the payment | Enter the payment id and verify it | Valid Payment id | Able to download the receipt | Order receipt downloaded | Pass
TC_DEMO_48 |  | To verify that user is able to download the receipt before payment | User must have payment id | Not able to download the receipt without payment id | Verify using payment id | Valid Payment id | Not able to download the receipt | Message appers "Please complete the payment first" | Pass
TC_DEMO_49 |  | To verify that download button is functioning or not | User completed all the requirement for downloading | User is able to click on the button after successful payment | Button highlighted after payment confirmation | N/A | Click able download button appers | User is able to download the receipt | Pass
TC_DEMO_50 |  | To verify that print button is functioning or not | User completed all the requirement for printing the receipt | User is able to click on the button after successful payment | Button highlighted after payment confirmation to print the receipt | N/A | Click able print receipt button appers | User is able to print the receipt | Pass

## Defect Report
Defect Id. | Module name | Defect Summary | Description | Actual Output | Defect Priority | Assigned To | Status
DF_DEMO_01 | Product | User is not able to remove the product from cart. | 1. User should be on the home page of Demoblaze. 2. Click on "Cart" option. 3. Click on the "Delete" option of which product wants to be removed. | The product gets removed from the cart. | High | ramya.gunashekar.29@gamil.com | Active
DF_DEMO_02 | Product | User is able to make payment inspite of invalid card number | 1. Enter Name on Card 2. Enter Card Number 3. Enter expiry date 4. Enter CVV | The entered details are used to make payment and order has been placed and system shows payment reciept. | Critical | ramya.gunashekar.29@gamil.com | Active
DF_DEMO_03 | Product | User isn't able to cancel order | 1.enter orders page 2.select the product 3.click on cancel order button | Order is Cancelled. | High | ramya.gunashekar.29@gamil.com | Active
DF_DEMO_04 | Search | User cannot able to see appropriate result for some keywords | 1.Product Name:Cell phone 2.click on search button | Genuine Leather Handbag with Cell Phone Holder & Many Pockets | High | ramyabharathi22032@gmail.com | Active

## Traceability matrix
Req ID | Req Description | Test Case Id | Status
RQ 01 | Verify Registration functionality | TC1 | Pass
|  | TC2 | Pass
|  | TC3 | PASS
|  | TC4 | PASS
|  | TC5 | PASS
|  | TC6 | PASS
|  | TC7 | PASS
|  | TC8 | PASS
|  | TC9 | PASS
|  | TC10 | PASS
|  | TC11 | Pass
RQ 02 | Verify Login functionality | TC12 | Pass
|  | TC13 | Pass
|  | TC14 | Pass
|  | TC15 | Pass
|  | TC16 | pass
|  | TC17 | pass
|  | TC18 | pass
|  | TC19 | Pass
|  | TC20 | pass
|  | TC21 | Pass
|  | TC22 | pass
|  | TC23 | pass
|  | TC24 | Pass
RQ 03 | Verify Search functionality | TC25 | Pass
|  | TC26 | Pass
|  | TC27 | Pass
|  | TC28 | Pass
|  | TC29 | Pass
|  | TC30 | Fail
|  | TC31 | Pass
|  | TC32 | Pass
|  | TC33 | Pass
|  | TC34 | Pass
RQ 05 | User should be able to add/remove product from cart. | TC35 | Pass
|  | TC36 | Fail
RQ 06 | User should be able to place the order. | TC37 | Pass
RQ 07 | User should be able to add shipping details. | TC38 | Pass
|  | TC39 | Pass
|  | TC40 | Pass
RQ 08 | User should be able to choose payment option. | TC41 | Fail
|  | TC42 | Pass
RQ 09 | User should be able to cancel the order. | TC43 | Fail
RQ 10 | Verify Receipt functionality | TC44 | Pass
|  | TC45 | Pass
|  | TC46 | Pass
|  | TC47 | Pass
|  | TC48 | Pass
RQ 11 | Download and Print button | TC49 | Pass
|  | TC50 | Pass

## summary report
Test Summary Report
Test Cycle System Test
EXECUTED | 50 | PASSED | 46
|  | FAILED | 4
|  | (Total)TESTS EXCUTED (PASSED+FAILED) | 50
PENDIING |  | 4
IN PROGRESS |  | 0
BLOCKED |  | 0
(Sub-Total) TEST PLANNED
(PENDING+INPROGRESS+BLOCKED+TEST+EXECUTED)
Function | Description | No of TCs Executed | No of TCs Passed | TCs Pending | Priority | Remarks
Registration Functionalities | Verify that user should be able to register to https://demowebshop.com/ succesfully. | 11 | 11 | 0 | High
Login Functionalities | Verify that user Should able to loginand able to see the products | 13 | 13 | 0 | High
Search Functionalities | Verify that user should able to access account and serach the products succesfully. | 10 | 9 | 1 | High
View Product module | Verify the User Should able to view products and access succesfully. | 9 | 6 | 3 | High
Download the receipt | Verify the user should able to download the recepit | 7 | 7 | 0 | High

## Sprint 2
Automation Testing Case Study
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: http://phptravels.net/
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Identify the Manual Test Cases that you want to automate. | 1. Creation of Project Structure
| 2. Plan the flow of application that you want to test using automation test scripts. | 2. Creation of Feature File.
3. Create a Maven Project - Associate required libraries with the Maven Project
4. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
5. Creation of Feature File
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin continue. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Test Runner class Parameters
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Report File Names
3. Design the test runner class
Sprint Day 3 | 1. Implement parametrization using apache POI | 1. Parametrization Sample Data :
| 2. Implement TestNG for generating reports and XML file for parallel execution of test suite | 2. Report File Names
| 3. Generate Step Definitions and write the Tests addressing all the functional requirements. | 3. Generating Step Defination File
Sprint Day 4 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 5 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements Continue | 1. Detail Test Script in Step Definitions
2. Feature File- Test Case – PF/OR collation in an Excel sheet
Sprint Day 6 | 1. Generate TestNG/XML Test report mentioning pass/fail status.
1. Test Reports
Sprint Day 7 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 8 | Sprint Evaluation